## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nitin Patel | 2026-08-11 | POST /api/evaluate endpoint returned 500 when request payload omitted the ai_response field | Sprint 1 | Nitin Patel | Logical | Added Pydantic Field validation with required constraint and descriptive 400 Bad Request error response | 2026-08-11 | Closed | Verified with empty string and missing field test cases
2 | Nitin Patel | 2026-08-14 | Hugging Face datasets library threw ArrowTypeError when loading SQuAD validation split on Python 3.13 | Sprint 1 | Nitin Patel | Others | Switched to canonical squad validation split and parsed question-context pairs directly into standard dictionary format | 2026-08-15 | Closed | Extracted 1,000 QA context pairs without schema errors
3 | Nitin Patel | 2026-08-18 | PyTorch and TensorFlow DLL collision on Windows caused Python process crash during sentence-transformers embedding generation | Sprint 1 | Nitin Patel | Others | Configured USE_TF=0 and USE_TORCH=1 environment variables before importing sentence-transformers | 2026-08-18 | Closed | Resolved C++ runtime lockup on Windows
4 | Nitin Patel | 2026-08-21 | PyMuPDF text extraction failed with unhandled exception when processing empty or scan-only PDF pages | Sprint 1 | Nitin Patel | Logical | Added text length check per page with fallback warning if extracted text is empty | 2026-08-22 | Closed | Prevents pipeline crash on blank document pages
5 | Nitin Patel | 2026-08-25 | Frontend evaluation pipeline progress indicator remained spinning after backend returned evaluation verdict | Sprint 1 | Nitin Patel | User Interface | Updated pipeline state check to transition step indicator to static checkmark on step 6 completion | 2026-08-25 | Closed | Progress bar transitions cleanly to 100% completed state
6 | Nitin Patel | 2026-09-01 | Relevance Judge score occasionally exceeded 5.0 boundary or returned float with excessive decimal places | Sprint 2 | Nitin Patel | Logical | Clamped score with min(5.0, max(1.0, raw_score)) and rounded to 1 decimal place | 2026-09-01 | Closed | Verified score remains strictly between 1.0 and 5.0 across varied queries
7 | Nitin Patel | 2026-09-04 | Accuracy Agent incorrectly marked out-of-domain questions as PASS by hallucinating facts from general LLM pretraining | Sprint 2 | Nitin Patel | Logical | Added strict closed-world grounding check returning Insufficient Evidence / Unverified when grounding chunks are empty | 2026-09-05 | Closed | Verified out-of-domain query returns UNVERIFIED status with notice banner
8 | Nitin Patel | 2026-09-08 | Gemini API returned 404 NotFound on deprecated gemini-2.0-flash model causing validation pipeline failure | Sprint 2 | Nitin Patel | Others | Updated primary model to gemini-3.6-flash and added multi-model fallback across 3.7-flash and 3.1-flash-lite | 2026-09-08 | Closed | Resolved model deprecation with seamless fallback
9 | Nitin Patel | 2026-09-10 | All 4 Overview tab cards rendered with uneven heights and staggered alignment due to column wrapping | Sprint 2 | Nitin Patel | User Interface | Replaced staggered column wrappers with direct 2x2 CSS Grid using grid-auto-rows: 1fr and equal stretch | 2026-09-11 | Closed | All 4 overview boxes render with identical height and clean symmetry
10 | Nitin Patel | 2026-09-11 | Hallucination Agent only flagged entire response without breaking down individual unsupported or fabricated statements | Sprint 2 | Nitin Patel | Logical | Added statement-by-statement extraction with Supported, Unsupported, Fabricated, and Contradictory classifications | 2026-09-12 | Closed | Each claim displays distinct highlight badge, cited evidence, and violation reason
11 | Nitin Patel | 2026-09-15 | Completeness Agent failed to penalize partially addressed multi-part questions when AI response used conversational filler | Sprint 3 | Nitin Patel | Logical | Updated prompt with specific omission breakdown and negative constraint checking against query clauses | 2026-09-15 | Closed | Verified with multi-part science and history test questions
12 | Nitin Patel | 2026-09-16 | Verdict Agent composite score displayed IEEE 754 floating point precision anomalies in UI summary | Sprint 3 | Nitin Patel | User Interface | Rounded composite score to 2 decimal places in backend verdict_agent.py and applied safeScore formatting in frontend | 2026-09-16 | Closed | Weighted score renders cleanly as 4.33 / 5.00
13 | Nitin Patel | 2026-09-17 | CSV Batch upload failed silently when file contained empty trailing rows or unescaped comma characters | Sprint 3 | Nitin Patel | Logical | Added csv.Sniffer dialect detection, non-empty row filtering, and strip whitespace preprocessing in parse_csv | 2026-09-17 | Closed | Successfully parses CSV files with blank lines and commas in text fields
14 | Nitin Patel | 2026-09-18 | Analytics Dashboard KPI cards displayed NaN when database had zero evaluation records in selected date range | Sprint 3 | Nitin Patel | User Interface | Added null-coalescing defaults (0 count, 0.0 avg score) and empty-state guidance illustrations | 2026-09-18 | Closed | Dashboard renders zero-state gracefully without calculation errors
15 | Nitin Patel | 2026-09-19 | Inspect modal triggered unhandled JavaScript TypeError (.map is not a function) when inspecting records during active batch evaluation | Sprint 3 | Nitin Patel | User Interface | Added safeList, safeScore, and safeParseJson helpers, parsed DB JSON strings, and wrapped modal in InspectErrorBoundary | 2026-09-20 | Closed | Inspect modal opens cleanly without screen blanking even during active batch runs
16 | Nitin Patel | 2026-09-20 | Evaluation pipeline latency reached 90 seconds due to 429 quota exhaustion and 20s gRPC retry loops on gemini-3.6-flash | Sprint 3 | Nitin Patel | Others | Switched PRIMARY_MODEL to gemini-3.1-flash-lite, configured dual API key rotation, and set request timeouts | 2026-09-20 | Closed | Evaluation latency reduced from 90s to 5.18s with all 5 independent agents intact
17 | Nitin Patel | 2026-09-21 | Radar chart label text on left and right axes ('Completeness', 'Accuracy') clipped at outer edge of SVG container | Sprint 4 | Nitin Patel | User Interface | Expanded radar viewBox to 390x270, centered radarCx to 195, and offset label coordinates with textAnchor alignment | 2026-09-21 | Closed | Verified labels render with ample margin on both 1366px and 1920px displays
18 | Nitin Patel | 2026-09-21 | Donut chart verdict distribution legend descriptions truncated prematurely with CSS text-overflow ellipsis | Sprint 4 | Nitin Patel | User Interface | Rebalanced flex ratios, removed restrictive max-width constraint, and crafted concise status descriptions | 2026-09-22 | Closed | Full text visible for all 4 verdict categories without trailing ellipsis
19 | Nitin Patel | 2026-09-22 | Batch evaluation Inspect modal exhibited horizontal scrollbar and rendered raw stringified JSON dictionaries for verified and flagged claims | Sprint 4 | Nitin Patel | User Interface | Replaced JSON.stringify with structured claim cards, added formatAspectText helper, set grid minmax(0, 1fr), and set overflow-x: hidden | 2026-09-23 | Closed | Modal displays formatted cards with badges and sources; zero horizontal scroll
20 | Nitin Patel | 2026-09-23 | API rate limits encountered during heavy consecutive batch evaluations when relying strictly on single LLM provider free-tier quota | Sprint 4 | Nitin Patel | Others | Integrated OpenAI GPT-4o-mini provider fallback alongside Gemini key rotation with unified response adapter | 2026-09-23 | Closed | Batch runs fail over seamlessly without hitting 429 quota exhaustion
21 | Nitin Patel | 2026-09-23 | Batch evaluation PDF report lacked granular question-by-question breakdown table with individual agent scores | Sprint 4 | Nitin Patel | Logical | Enhanced report_generator.py to build multi-page tables listing question excerpts, agent scores, composite, and final verdicts | 2026-09-24 | Closed | PDF export generates comprehensive audit report with executive KPIs and itemized details
22 | Nitin Patel | 2026-09-24 | Global branding inconsistency across browser title, top navigation, sidebar, and favicon prior to final presentation | Sprint 4 | Nitin Patel | User Interface | Rebranded platform to SentryAI, updated HTML titles, headers, footers, and replaced default Vite icon with custom SentryAI shield/iris SVG | 2026-09-24 | Closed | Unified SentryAI identity active across all browser surfaces and reports
23 | Nitin Patel | 2026-09-25 | Analytics Dashboard threw 500 Internal Server Error when selecting Pass/Fail verdict filters due to unescaped % character in psycopg2 SQL query | Sprint 4 | Nitin Patel | Logical | Refactored SQL query in get_analytics_summary to use parameterized LIKE %s placeholders with tuple params | 2026-09-25 | Closed | Parameterized queries active; verified zero SQL exceptions across all verdict filters
24 | Nitin Patel | 2026-09-25 | Batch, Verdict, and Model Engine dropdowns in Analytics Dashboard rendered with unstyled OS native dropdown controls and white option menus | Sprint 4 | Nitin Patel | User Interface | Restyled filter bar with custom glassmorphic pill cards, SVG chevrons, theme-consistent dark option backgrounds, and active border glow | 2026-09-26 | Closed | Custom styled glassmorphism dropdowns active with SVG icons and dark theme styling
25 | Nitin Patel | 2026-09-26 | Analytics Model Engine filter did not separate OpenAI and Gemini evaluation results because model selection was not persisted as a dedicated database column | Sprint 4 | Nitin Patel | Logical | Added ai_engine VARCHAR(64) column to evaluation_records and batch_evaluations tables and updated save_evaluation and create_batch_job | 2026-09-27 | Closed | ai_engine column added to schema; per-model filtering fully operational
26 | Nitin Patel | 2026-09-26 | Single and Batch PDF reports lacked dynamic total page numbering (Page X of Y) and running header on subsequent pages | Sprint 4 | Nitin Patel | User Interface | Implemented custom NumberedCanvas class in report_generator.py to calculate two-pass page counts and render running headers and footers | 2026-09-27 | Closed | NumberedCanvas two-pass page numbering and running headers verified across all PDF reports

## Sheet2
Logical
User Interface
Maintainability
Standards
Others